## Sheet1
Appendix A: Project Schedule
Critical Path
Parallel Path
| 2016 | [10 empty] | 2017 | [10 empty] | 2018
Event | Jan | Feb | March | April | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | April | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | April | June | July | Aug | Sep | Oct | Nov | Dec
CDA approval to proceed | bar: 2016 Jan
Concept Phase + Community Design Process | bar: 2016 Feb to 2016 April
Concept Review, Revisions and Approvals | bar: 2016 June to 2016 July
Additional Grant Applications | bar: 2016 Feb to 2016 July; 2017 Sep to 2017 Dec
ACSO Mobilization of temporary landuse | bar: 2016 April to 2017 Jan
Establishment & Opening of Community Garden | bar: 2016 June to 2018 Dec
Phase 1&2 Schematic Design kick-off | bar: 2016 Aug
Phase 1&2 Schematic Design | bar: 2016 Aug to 2016 Sep
Phase 1 Design Development (Including reviews) | bar: 2016 Sep to 2016 Nov
Phase 1 Construction Documents | bar: 2016 Nov to 2016 Dec
Phase 1 Bid | bar: 2017 Jan
Phase 1 Mobilization and Demo | bar: 2017 Feb to 2017 March
Phase 1 Construction | bar: 2017 April to 2017 Aug
Phase 2 Design Development (Including reviews) | bar: 2018 Jan to 2018 March
Phase 2 Construction Documents | bar: 2018 March to 2018 April
Phase 2 Bid | bar: 2018 June
Phase 2 Mobilization and Demo | bar: 2018 July to 2018 Aug
Phase 2 Construction | bar: 2018 Sep to 2018 Dec
ACSO Operation of permanent facilities | bar: 2017 Aug to 2018 Dec