COUNTY OF ALAMEDA

REQUEST FOR PROPOSALS

for

The <Housing Element of the General Plan

Contact Person: Liz McElligott, Assistant Planning Director Phone Number: (510) 670-5400 E-mail Address: elizabeth.mcelligott@acgov.org

RESPONSE DUE

by

5:00 p.m.

on

January 26, 2022

via email as PDF

elizabeth.mcelligott@acgov.org

for

Alameda County Community Development Agency

224 W. Winton Avenue, Room. 111

Hayward, CA 94544

Alameda County is committed to reducing environmental impacts across our entire supply chain.

If printing this document, please print only what you need, print double-sided, and use recycled-content paper.

# CALENDAR OF EVENTS

REQUEST FOR PROPOSAL

<HOUSING ELEMENT

| EVENT | DATE/LOCATION |
| --- | --- |
| Request Issued | December 15, 2021 |
| Networking Conference #1 | January 5, 2022 at 2:00 p.m. Please click the link to join the Zoom meeting: https://us02web.zoom.us/j/81356832175 Webinar ID: 813 5683 2175 To join by Phone ONLY: 1 (669) 900-9128 or 1 (346) 248-7799 |
| Networking Conference #2 | January 7, 2022 at 10:00 a.m. Please click the link to join the Zoom meeting: https://us02web.zoom.us/j/81356832175 Webinar ID: 813 5683 2175 To join by Phone ONLY: 1 (669) 900-9128 or 1 (346) 248-7799 |
| Written Questions Due via Email: elizabeth.mcelligott@acgov.org | January 10, 2022 by 5:00 p.m. |
| List of Attendees | January 10, 2022 |
| Q&A Issued | January 12, 2022 |
| Addendum Issued (only if necessary, to amend RFP) | January 12, 2022 |
| Response Due | January 26, 2022 by 5:00 p.m. |
| Evaluation Period | January 27 – 31, 2022 |
| Vendor Interviews | February 4, 2022 |
| Notice of Intent to Award Issued | February 7, 2022 |
| Board Consideration Award Date | March 1, 2022 |
| Contract Start Date | March 1, 2022 |

NOTE:  All dates are tentative and subject to change.

COUNTY OF ALAMEDA

REQUEST FOR PROPOSAL

SPECIFICATIONS, TERMS & CONDITIONS

for

HOUSING ELEMENT

TABLE OF CONTENTS

Page

CALENDAR OF EVENTS	1

I.	STATEMENT OF WORK	5

A.	INTENT	5

B.	SCOPE	5

C.	BACKGROUND	6

D.	BIDDER QUALIFICATIONS	6

E.	SPECIFIC REQUIREMENTS	6

F.	DELIVERABLES / REPORTS	9

G.	NETWORKING / BIDDERS CONFERENCES	11

II.	COUNTY PROCEDURES, TERMS, AND CONDITIONS	12

H.	EVALUATION CRITERIA / SELECTION COMMITTEE	12

I.	CONTRACT EVALUATION AND ASSESSMENT	16

J.	NOTICE OF INTENT TO AWARD	16

K.	TERM / TERMINATION / RENEWAL	17

L.	PRICING	17

M.	AWARD	18

N.	METHOD OF ORDERING	19

O.	WARRANTY	20

P.	INVOICING	20

Q.	LIQUIDATED DAMAGES	20

R.	PERFORMANCE REQUIREMENTS	21

S.	ACCOUNT MANAGER / SUPPORT STAFF	21

III.	INSTRUCTIONS TO BIDDERS	21

T.	COUNTY CONTACTS	21

U.	SUBMITTAL OF BIDS	22

V.	RESPONSE FORMAT	23

ATTACHMENTS

EXHIBIT A BID RESPONSE PACKET

EXHIBIT B MAP OF URBAN UNINCORPORATED COMMUNITIES

EXHIBIT C INSURANCE REQUIREMENTS

# STATEMENT OF WORK

## INTENT

It is the intent of these specifications, terms and conditions to describe an experienced and qualified consultant to assist County Staff with the preparation and adoption of a revised Housing Element, related rezoning, and all necessary environmental review as required under state law, in a manner consistent with the Regional Housing Needs Allocation 6 (RHNA 6) planning period (2023-2031).

The County intends to award a one-year, 10-month contract to the Bidder(s) selected as the most responsible Bidder(s) whose response conforms to the RFP and meets the County’s requirements. The contract is expected to begin in March 2022 and conclude by December 2023.

## SCOPE

The County is seeking assistance from a contractor with the experience, capacity and skills necessary to develop, draft and finalize a revised Housing Element for Unincorporated Alameda County, to ensure there will be extensive and diverse community input throughout each phase of work, and to take the Housing Element through the public consultation process to adoption by the County Board of Supervisors and certification by the State Department of Housing and Community Development (State HCD). In addition, the contractor will be expected to complete rezonings as necessary to accommodate the County’s Cycle 6 RHNA and prepare a program-level environmental impact report (EIR) for the Housing Element and rezonings with sufficient detail to reduce or eliminate the need for site-specific environmental review for future residential development projects. The contractor will be expected to work closely with staff from the County Community Development Agency’s (CDA) Planning and Housing and Community Development Departments, and coordinate with State HCD to help ensure ultimate certification of the updated element.

The County has allocated $500,000 in Local Early Action Planning (LEAP) grant funds for the project. Consideration will be given to the proposal that outlines the most efficient and cost-effective way to perform the work and provide the services described in this RFP.

Through Alameda County’s engagement in a countywide collaborative and ABAG’s Regional Housing Technical Assistance Program, we anticipate a reduction in costs for some core tasks, as detailed below. The collaborative is supported by an approximately half time technical assistance provider, who will produce draft material for some sections of the Housing Element that are similar throughout the County, as noted below. Respondents should be prepared to use and/or adapt this material as appropriate, and factor that into their proposal. Details about what is included in the scope of work is provided in Section E – Specific Requirements.

## BACKGROUND

Alameda County’s current housing element was certified by State HCD in May of 2015 and is available on the County website here. Annual Progress Reports prepared in compliance with Government Code Section 65400(b)(1) are available here. Exhibit B contains a map of the urban unincorporated communities within the County.

At the same time as the update to the Housing Element, the County will also be working on an Environmental Justice Element to comply with SB 1000, as well as updates to the Community Climate Action Plan and the Safety Element of the County General Plan. A consultant for the Environmental Justice Element project has already been selected. An RFP has been issued for the Community Climate Action Plan and the Safety Element project. Proposals for that project are due January 7, 2022.

Preparing the housing sites inventory for the revised Housing Element is anticipated to be a major portion of the project. The County’s Cycle 6 Regional Housing Needs Allocation (RHNA) is 4,711 housing units, a 166% increase from the County’s Cycle 5 RHNA of 1,769 housing units. In addition, recent state legislation placed substantial restrictions on parcels that may be included in the inventory. These limitations are likely to impact the County’s ability to identify adequate sites to meet its RHNA obligation given the lack of vacant land available within the County’s Urban Growth Boundary. To ensure an adequate inventory of viable sites, we anticipate the element update will necessitate rezoning in targeted areas.

## BIDDER QUALIFICATIONS

BIDDER Minimum Qualifications

Bidder shall be regularly and continuously engaged in the business of providing land use planning services and stakeholder and community engagement for at least three (3) years.

Bidder shall possess all permits, licenses and professional credentials necessary to supply product and perform services as specified under this RFP.

## SPECIFIC REQUIREMENTS

The selected Contractor(s) will have demonstrated expertise in land use planning and conducting stakeholder engagement and community outreach, especially among low-income and underserved communities (i.e. seniors, the disabled, persons with limited English proficiency, etc.). The Contractor(s) will be expected to become familiar with the unincorporated communities, the County’s General Plan, and zoning ordinance, and work closely in collaboration with CDA staff.

Proposals must address the following tasks, providing a description and timeline of how they would be accomplished. Additional or optional tasks may be included and creative approaches are welcome. The final scope of work will be subject to refinement and mutual agreement following the project’s launch and further discussion. The scope of work for these tasks is anticipated to include, but is not limited to, the work detailed below, and the Deliverables/ Reports identified in Section F.

- Project Management and Coordination

Develop a process to manage the project, including communication and coordination between the consultant and County staff via meetings, phone conferences, email exchanges, and other communications to ensure timely delivery and adoption of the County’s updated housing element. Proposal should identify the number of meetings anticipated and expectations for County staff. Strategies or practices to ensure clear and timely communication and effective project coordination should be described. Strategies for ensuring coordination with State HCD over the course of the project should also be addressed, as needed.

- Community Outreach and Engagement

Develop a program that effectively reaches, educates and engages the community throughout the Housing Element update. Include strategies to ensure broad inclusion, particularly of hard to reach groups and special needs populations, with special attention given to communicating information so it is accessible and easy to understand. Outreach is expected to begin early in the process and continue throughout for feedback on important topics such as draft ideas, site options, the draft Housing Element and environmental reviews. Please discuss options for virtual as well as in person meetings, depending on changing safety considerations. Consultant should lead the engagement as well as providing a summary of the work.

- Housing and Special Housing Needs

ABAG’s Regional Housing Technical Assistance Program will provide jurisdiction-specific graphs and write-ups for all required data, including population, demographic, housing, market conditions and regional comparisons. Adapt the material from ABAG as needed for inclusion in the Housing Element

- Housing Constraints

Using relevant information provided by ABAG’s Regional Housing Technical Assistance Program, identify potential and actual governmental and nongovernmental constraints for the preservation, protection or production of housing across income levels within the County.

- Existing Housing Element

Review the current Housing Element and identify the County’s success in implementing the identified goals, policies and programs; and provide explanations and updates where goals, policies or programs are in progress, have been abandoned or have not proven effective.

- Sites Inventory

Using the Housing Element Site Selection (HESS) Tool provided by ABAG, prepare the sites inventory section of the Housing Element, demonstrating how the County will satisfy its RHNA in each income category. This includes identifying safe assumptions, evaluating sites and analyzing potential policy strategies to increase site capacity, demonstrating development viability (per State law) and inputting the information into HCD’s electronic form for submittal with the updated element. We anticipate that this will be the most significant area of work for the update process, and will need to start early in order to ensure adequate time for consideration of potential areas for rezoning or other changes to development standards needed to achieve the RHNA.

- Goals, Policies, Programs and Quantified Objectives

Identify goals, policies, programs and quantified objectives to include in the Housing Element to ensure compliance with State law and effective response to the housing needs, constraints and key priorities identified through the update process. This task includes ensuring responsiveness to priorities articulated through the community engagement process as well as ensuring internal consistency with other elements of the General Plan. This task will include identification of other General Plan policy updates or revisions needed to ensure consistency.

- Rezoning

Based on the sites analyses, work with County staff to identify potential areas for rezoning, if necessary. This must include consideration of the State requirement for maintaining an adequate housing sites inventory throughout the eight-year planning period.

- Draft Housing Element and Public Hearings

Prepare and submit an administrative draft Housing Element for County staff review. Staff will provide a comprehensive set of desired changes. Once edits are complete, prepare a draft Housing Element that is made available to the public and presented to Castro Valley, Eden, and Fairview Municipal Advisory Councils (MAC’s), Planning Commission, Board of Supervisors Committees (Transportation/Planning Committee, and Unincorporated Services Committee) and Board of Supervisors at public hearings. Based on Commission and Board input, prepare a HCD review draft and submit to HCD for the mandated review.

- Final Draft Hearings, Final Adoption and Certification

The consultant will work closely with HCD and County staff to respond to any comments, and produce a final draft housing element for adoption. Present to the Castro Valley, Eden, and Fairview Municipal Advisory Councils (MAC’s), Planning Commission, Board of Supervisors Committees (Transportation/Planning Committee, and Unincorporated Services Committee) and Board of Supervisors at public hearings. Prepare the final Housing Element, including any changes from the public hearings, and submit to HCD for final certification as well as applicable water and sanitary districts and the California Office of Planning and Research.

- CEQA Documentation

Prepare all required documents for California Environmental Quality Act (CEQA) review and submittal, including the Initial Study, Mitigated Negative Declaration or Environmental Impact Report and CEQA Determination, for the Housing Element and any necessary rezonings. This should include public posting and noticing for comment. For budget purposes, consultant may list different prices depending on the level of analysis that may ultimately be needed.

## DELIVERABLES / REPORTS

The following deliverables correspond to the Tasks above. As identified above, the Contractor(s) shall provide the County Staff Project Team the opportunity to review and comment on all deliverables at least three (3) times.

Task 1 - Project Management and Coordination:

- Plan for communication with county staff

- Project Schedule

- Weekly Progress Reports

- Invoicing & Budget Updates

Task 2 - Community Outreach and Engagement:

At a minimum outreach should consist of:

- Initial presentation to Planning Commission and Board of Supervisors Unincorporated Services Committee

- Presentation to the Castro Valley, Eden, and Fairview Municipal Advisory Councils (MAC’s)

- Online/virtual participation opportunities

Task 3 - Housing and Special Housing Needs:

- Housing and Special Housing Needs section for Draft Housing Element

Task 4 - Housing Constraints:

- Housing Constraints section for Draft Housing Element

Task 5 - Existing Housing Element:

- Analysis of implementation of the existing element for Draft Housing Element

Task 6 - Sites Inventory:

- Sites Inventory section for Draft Housing Element.

Task 7 - Goals, Policies, Programs and Quantified Objectives:

- Goals, Policies, Programs and Quantified Objectives section for Draft Housing Element

Task 8 - Rezoning:

- List of properties proposed for rezoning

- Supporting documentation and meeting-related documents

Task 9 - Draft Housing Element and Public Hearings:

- Administrative draft and draft housing element (Microsoft Word)

- PowerPoint

- Two public hearings

Task 10 - Final Draft Hearings, Final Adoption and Certification:

- Draft final and final housing element (Microsoft Word and PDF)

- PowerPoint

- Two public hearings

Task 11  CEQA Documentation

      - Initial Study

      - Mitigated Negative Declaration or Environmental Impact Report

      - CEQA Determination

      - Public posting and noticing as required by state law

      - Meeting-related documents

## NETWORKING / BIDDERS CONFERENCES

The Bidders conference held on January 5 and 7, 2022 will be online via Zoom ONLY. Interviews will NOT be in person due to COVID compliance.

Networking/Bidders conferences will be held to:

Provide an opportunity for Small Local Emerging Businesses (SLEBs) and large firms to network and develop subcontracting relationships in order to participate in the contract(s) that may result from this RFP

Provide an opportunity for Bidders to ask specific questions about the project and request RFP clarification

Provide the County with an opportunity to receive feedback regarding the project and RFP.

The list of Bidder conference attendees will be released in a separate document.

Only written questions submitted by the stated deadline will be addressed in an RFP Question and Answer (Q&A) following the Networking/Bidders conferences.  Should there be a need to amend or revise the RFP, an addendum will be issued following the Networking/Bidders Conferences. The Q&A and Addendum are the final stance of the County.

All questions regarding these specifications, terms and conditions are to be submitted in writing via e-mail by 5:00 p.m. on January 10, 2022 to:

Liz McElligott, Assistant Planning Director

Alameda County Planning Department

E-Mail:  elizabeth.mcelligott@acgov.org

PHONE: (510) 670-5400

Potential Bidders are strongly encouraged to attend Networking/Bidders Conference(s) in order to facilitate potential subcontracting relationships.  Vendors who attend a Networking/Bidder’s Conference will be added to the Vendor Bid List. Failure to participate in a Networking/Bidder’s Conference will in no way relieve the Contractor from furnishing goods and/or services required in accordance with these specifications, terms and conditions. Attendance at a Networking/Bidder’s Conference is highly recommended but is not mandatory.

# COUNTY PROCEDURES, TERMS, AND CONDITIONS

## EVALUATION CRITERIA / SELECTION COMMITTEE

All proposals that pass the initial Evaluation Criteria which are determined on a pass/fail basis will be evaluated by a County Selection Committee (CSC).  The County Selection Committee may be composed of County staff and other parties that may have expertise or experience in land use planning, housing, and community outreach services. The CSC will score and recommend a Contractor in accordance with the evaluation criteria set forth in this RFP.  Other than the initial pass/fail Evaluation Criteria, the evaluation of the proposals shall be within the sole judgment and discretion of the CSC.

Bidders shall neither contact nor lobby evaluators during the evaluation process.  Attempts by Bidders to contact and/or influence members of the CSC may result in disqualification of Bidder.

The CSC will evaluate each proposal meeting the qualification requirements set forth in this RFP.  Bidders should bear in mind that any proposal that is unrealistic in terms of the technical or schedule commitments, or unrealistically high or low in cost, will be deemed reflective of an inherent lack of technical competence or indicative of a failure to comprehend the complexity and risk of the County’s requirements as set forth in this RFP.

Bidders are advised that in the evaluation of cost it will be assumed that the unit price quoted is correct in the case of a discrepancy between the unit price and an extension.

As a result of this RFP, the County intends to award a contract to the responsible Bidders whose response conforms to the RFP and whose bid presents the greatest value to the County, all evaluation criteria considered.  The combined weight of the evaluation criteria is greater in importance than cost in determining the greatest value to the County.  The goal is to award a contract to the Bidder(s) that proposes the County the best quality as determined by the combined weight of the evaluation criteria.  The County may award a contract of higher qualitative competence over the lowest priced response.

The basic information that each section should contain is specified below, these specifications should be considered as minimum requirements.  Much of the material needed to present a comprehensive proposal can be placed into one of the sections listed. However, other criteria may be added to further support the evaluation process whenever such additional criteria are deemed appropriate in considering the nature of the services being solicited.

Each of the Evaluation Criteria below will be used in ranking and determining the quality of Bidders’ proposals.  Proposals will be evaluated according to each Evaluation Criteria and scored on the zero to five-point scale outlined below.  The scores for all Evaluation Criteria will then be added, according to their assigned weight (below), to arrive at a weighted score for each proposal.  A proposal with a high weighted total will be deemed of higher quality than a proposal with a lesser-weighted total.  The final maximum score for any project is 550 points, including the possible 50 points for local and small, local and emerging, or local preference points (maximum 10% of final score).

The evaluation process may include a two-stage approach including an initial evaluation of the written proposal and preliminary scoring to develop a short list of Bidders that will continue to the final stage of oral interview and reference checks.  The preliminary scoring will be based on the total points, excluding points allocated to references and oral interview.

If the two-stage approach is used, the three (3) Bidders receiving the highest preliminary scores and with at least 200 points will be invited to an oral interview.  Only the Bidders meeting the short list criteria will proceed to the next stage.  All other Bidders will be deemed eliminated from the process.  All Bidders will be notified of the short list participants; however, the preliminary scores at that time will not be communicated to Bidders.

The zero to five-point scale range is defined as follows:

| 0 | Not Acceptable | Non-responsive, fails to meet RFP specification. The approach has no probability of success. If the unmet specification is a mandatory requirement, this score may result in disqualification of proposal. |
| --- | --- | --- |
| 1 | Poor | Below average, falls short of expectations, is substandard to that which is the average or expected norm, has a low probability of success in achieving objectives per RFP. |
| 2 | Fair | Has a reasonable probability of success, however, some objectives may not be met. |
| 3 | Average | Acceptable, achieves all objectives in a reasonable fashion per RFP specification. This will be the baseline score for each item with adjustments based on interpretation of proposal by Evaluation Committee members. |
| 4 | Above Average / Good | Very good probability of success, better than that which is average or expected as the norm. Achieves all objectives per RFP requirements and expectations. |
| 5 | Excellent / Exceptional | Exceeds expectations, very innovative, clearly superior to that which is average or expected as the norm. Excellent probability of success and in achieving all objectives and meeting RFP specification. |

The Evaluation Criteria and their respective weights are as follows:

|  | Evaluation Criteria | Weight |
| --- | --- | --- |
|  | Completeness of Response: Responses to this RFP must be complete. Responses that do not include the proposal content requirements identified within this RFP and subsequent Addenda and do not address each of the items listed below will be considered incomplete, be rated a Fail in the Evaluation Criteria and will receive no further consideration. | Pass/Fail |
|  | Debarment and Suspension: Bidders, its principal and named subcontractors are not identified on the list of Federally debarred, suspended or other excluded parties located at www.sam.gov/SAM/. | Pass/Fail |
|  | Cost: Proposal is determined to be within average cost range for the scope of work. | 15 Points |
|  | Understanding of the Project: Proposals will be evaluated against the RFP specifications and the questions below: Has the proposer demonstrated a thorough understanding of the purpose and scope of the project? How well has the proposer identified pertinent issues and potential problems related to the project? Has the proposer demonstrated that it understands the deliverables the County expects it to provide? Has the proposer demonstrated that it understands the County’s time schedule and can meet it? | 20 Points |
|  | Relevant Experience and Quality of Work: Proposals will be evaluated against the RFP specifications and the questions below: Do the individuals assigned to the project have experience on relevant projects? How extensive is the applicable education and experience of the personnel designated to work on the project, including with land use planning, housing, and equitable community engagement? Has the bidder demonstrated ability to design and implement an equitable Community Engagement Strategy in close partnership with CBO’s and community members? Does the bidder demonstrate the ability to provide multi-lingual communications? Has the bidder demonstrated expertise and experience in land use planning, facilitation and community engagement in low-income and underserved communities, including approaches necessary under COVID-19 local public health protocols, working with local government, conducting community engagement and multi-stakeholder planning processes? Has the bidder demonstrated sufficient familiarity with housing policies and strategies to translate technical concepts into education or outreach materials? | 20 Points |
|  | Methodology: Proposals will be evaluated against the RFP specifications and the questions below: Does the methodology depict a logical approach to fulfilling the requirements of the RFP? Does the methodology match and contribute to achieving the objectives set out in the RFP? Does the methodology interface with the County’s time schedule? | 20 Points |
|  | References (See Exhibit A – Bid Response Packet) | 10 Points |
|  | Oral Interview: The oral interview on the proposal shall not exceed 60 minutes. The oral interview may include responding to standard and specific questions from the CSC regarding the Bidder’s proposal. The scoring may be revised based on the oral interview. | 15 Points |
| SMALL LOCAL EMERGING BUSINESS PREFERENCE |
|  | Small and Local or Emerging and Local Preference: Points equaling five to ten percent of the Bidder’s total score, for the above Evaluation Criteria, will be added. This will be the Bidder’s final score for purposes of award evaluation. | 5 to 10% |

## CONTRACT EVALUATION AND ASSESSMENT

During the initial 60-day period of any contract which may be awarded to the Contractor, the County may review the proposal, the contract, any goods or services provided, and/or meet with the Contractor to identify any issues or potential problems.

The County reserves the right to determine, at its sole discretion, whether:

The contractor has complied with all terms of this RFP; and

Any problems or potential problems with the proposed goods and services were evidenced which make it unlikely (even with possible modifications) that such goods and services have met or will meet the County requirements.

If, as a result of such determination, the County concludes that it is not satisfied with Contractor, Contractor’s performance under any awarded contract and/or Contractor’s goods and services as contracted for therein, the Contractor will be notified that the contract is being terminated.  The contractor shall be responsible for returning County facilities to their original state at no charge to the County.  The County will have the right to invite the next highest ranked Bidder to enter into a contract.  The County also reserves the right to re-bid this project if it is determined to be in its best interest to do so.

## NOTICE OF INTENT TO AWARD

At the conclusion of the RFP response evaluation process (“Evaluation Process”), all Bidders will be notified in writing by e-mail, or US Postal Service mail, of the contract award recommendation, if any. The document providing this notification is the Notice of Intent to Award.

The Notice of Intent to Award will provide the following information:

The name of the Bidder being recommended for contract award; and

The names of all other parties that submitted proposals.

At the conclusion of the RFP response evaluation process and negotiations, debriefings for unsuccessful Bidders will be scheduled and provided upon written request and will be restricted to discussion of the unsuccessful offeror’s bid.  Under no circumstances will any discussion be conducted with regard to contract negotiations with the successful Bidder.

The submitted proposals shall be made available upon request no later than five calendar days before approval of the award and contract is scheduled to be heard by the Board of Supervisors.

## TERM / TERMINATION / RENEWAL

The term of the contract, which may be awarded pursuant to this RFP, will be one year and 10 months.

By mutual agreement, any contract which may be awarded pursuant to this RFP, may be extended for an additional one-year term at agreed prices with all other terms and conditions remaining the same.

## PRICING

All pricing as quoted will remain firm for the term of any contract that may be awarded as a result of this RFP.

Unless otherwise stated, Bidder agrees that, in the event of a price decline, the benefit of such lower price shall be extended to the County.

Any price increases or decreases for subsequent contract terms may be negotiated between Contractor and County only after completion of the initial term.

Taxes and freight charges:

The County is soliciting a total price for this project. The price(s) quoted shall be the total cost the County will pay for this project including all taxes (excluding Sales and Use taxes) and all other charges.

No charge for delivery, drayage, express, parcel post packing, cartage, insurance, license fees, permits, costs of bonds, or for any other purpose, except taxes legally payable by County, will be paid by the County unless expressly included and itemized in the bid.

Amount paid for transportation of property to the County of Alameda is exempt from Federal Transportation Tax.  An exemption certificate is not required where the shipping papers show the consignee as Alameda County; as such papers may be accepted by the carrier as proof of the exempt character of the shipment.

Articles sold to the County of Alameda are exempt from certain Federal excise taxes.  The County will furnish an exemption certificate.

All prices quoted shall be in United States dollars and "whole cent," no cent fractions shall be used.  There are no exceptions.

A total price is required for this contract and will be the maximum price the County will pay.

Price quotes shall include any and all payment incentives available to the County.

Bidders are advised that in the evaluation of cost, if applicable, it will be assumed that the unit price quoted is correct in the case of a discrepancy between the unit price and an extension.

Federal and State minimum wage laws apply.  The County has no requirements for living wages.  The County is not imposing any additional requirements regarding wages.

## AWARD

Proposals will be evaluated by a committee and will be ranked in accordance with the RFP section titled “Evaluation Criteria/Selection Committee.”

The committee will recommend award to the Bidder who, in its opinion, has submitted the proposal that best serves the overall interests of the County and attains the highest overall point score.  Award may not necessarily be made to the Bidder with the lowest price.

Small and Emerging Locally Owned Business:  The County is vitally interested in promoting the growth of small and emerging local businesses by means of increasing the participation of these businesses in the County’s purchase of goods and services.

As a result of the County’s commitment to advance the economic opportunities of these businesses, Bidders must meet the County’s Small and Emerging Locally Owned Business requirements in order to be considered for the contract award.  These requirements can be found online at: https://www.acgov.org/sleb/overview.htm

A small business is defined by the United States Small Business Administration (SBA) as having no more than the number of employees or average annual gross receipts over the last three years required per SBA standards based on the small business's appropriate NAICS code.

An emerging business is defined by the County as having either annual gross receipts of less than one-half that of a small business OR having less than one-half the number of employees AND that has been in business less than five years.

The County reserves the right to reject any or all responses that materially differ from any terms contained in this RFP or from any Exhibits attached hereto, to waive informalities and minor irregularities in responses received, and to provide an opportunity for Bidders to correct minor and immaterial errors contained in their submissions.  The decision as to what constitutes a minor irregularity shall be made solely at the discretion of the County.

Any proposal/bids that contain false or misleading information may be disqualified by the County.

The County reserves the right to award to a single or multiple Contractors.

The County has the right to decline to award this contract or any part thereof for any reason.

Board approval to award a contract is required.

A contract must be negotiated, finalized, and signed by the recommended awardee prior to Board approval.

Final Standard Agreement terms and conditions will be negotiated with the selected Bidder.  Bidder may access a copy of the Standard Services Agreement template can be found online at:

http://www.acgov.org/gsa/purchasing/standardServicesAgreement.pdf

The template contains minimal Agreement boilerplate language only.

The RFP specifications, terms, conditions and Exhibits, RFP Addenda and Bidder’s proposal, may be incorporated into and made a part of any contract that may be awarded as a result of this RFP.

## METHOD OF ORDERING

A written PO and signed Standard Agreement contract will be issued upon Board approval.

POs and Standard Agreements will be transmitted electronically or mailed and shall be the only authorization for the Contractor to place an order.

POs and payments for products and/or services will be issued only in the name of Contractor.

Contractor shall adapt to changes to the method of ordering procedures as required by the County during the term of the contract.

Change orders shall be agreed upon by Contractor and County and issued as needed in writing by County.

## WARRANTY

Bidder expressly warrants that all goods and services to be furnished pursuant to any contract awarded it arising from the Bid will conform to the descriptions and specifications contained herein.  Bidder expressly warrants that all goods and services to be furnished pursuant to such award will be fit and sufficient for the purpose(s) intended.  This warranty shall survive any inspections, delivery, acceptance or payment by the County.  Bidder warrants that all work and services furnished hereunder shall be guaranteed for a period of three (3) years from the date of acceptance by the County.

## INVOICING

Contractor shall invoice the requesting department, unless otherwise advised, upon satisfactory receipt of product and/or performance of services.

County will use best efforts to make payment within 30 days following receipt and review of invoice and upon complete satisfactory receipt of product and performance of services.

County shall notify Contractor of any adjustments required to invoice.

Invoices shall contain County PO number, invoice number, remit to address and itemized products and/or services description and price as quoted and shall be accompanied by acceptable proof of delivery.

Contractor shall utilize standardized invoice upon request.

Invoices shall only be issued by the Contractor who is awarded a contract.

Payments will be issued to and invoices must be received from the same Contractor whose name is specified on the POs.

The County will pay Contractor monthly or as agreed upon, not to exceed the total quoted in the bid response.

## LIQUIDATED DAMAGES

In the event the Contractor’s performance and/or deliverable projects have been deemed unsatisfactory by a review committee, the County reserves the right to withhold future payments until the performance and or deliverable projects are deemed satisfactory.

## PERFORMANCE REQUIREMENTS

    - Contractor shall comply with all the terms of this contract, as may be modified periodically at the sole discretion of the County Community Development Agency, including but not limited to providing all deliverables, attendance at all meetings and public hearings, staying within the budget, and meeting the letter and intent of the project scope.

    - Contractor shall comply with all scheduling and deadline requirements of this contract, as may be modified periodically at the sole discretion of the County Community Development Agency.

    - Contractor shall provide to the County Community Development Agency all documents in both .pdf, bound paper copies, and editable electronic file formats, to the satisfaction of the County Community Development Agency.

## ACCOUNT MANAGER / SUPPORT STAFF

Contractor shall provide a dedicated competent account manager who shall be responsible for the County account/contract.  The account manager shall receive all orders from the County and shall be the primary contact for all issues regarding Bidder’s response to this RFP and any contract which may arise pursuant to this RFP.

Contractor shall also provide adequate, competent support staff that shall be able to service the County during normal working hours, Monday through Friday.  Such representative(s) shall be knowledgeable about the contract, products and/or services offered and able to identify and resolve quickly any issues including but not limited to order and invoicing problems.

Contractor account manager shall be familiar with County requirements and standards and work with the Community Development Agency to ensure that established standards are adhered to.

# INSTRUCTIONS TO BIDDERS

## COUNTY CONTACTS

The Alameda County Planning Department is managing the competitive process for this project on behalf of the County.  All contact during the competitive process is to be through the Alameda County Planning Department only.

The evaluation phase of the competitive process shall begin upon receipt of bids until a contract has been awarded.  Bidders shall not contact or lobby evaluators during the evaluation process.  Attempts by Bidder to contact evaluators may result in disqualification of Bidder.

Contact Information for this RFP:

Liz McElligott, Assistant Planning Director

Alameda County Community Development Agency

Planning Department

224 W. Winton Avenue, Suite 111

Hayward, CA  94544

E-Mail:  elizabeth.mcelligott@acgov.org

PHONE: (510) 670-5400

## SUBMITTAL OF BIDS

All bids must be completed and successfully submitted by email ONLY to elizabeth.mcelligott@acgov.org BY 5:00 p.m. on the due date specified in the Calendar of Events.

Bidders must submit an electronic copy of their proposal. The electronic copy must be in a single file (PDF with Optical Character Recognition (OCR) preferred) and shall be an exact scanned image of the original hard copy Exhibit A – Bid Response Packet, including additional required documentation.

All costs required for the preparation and submission of a bid shall be borne by Bidder.

Only one bid response will be accepted from any one person, partnership, corporation, or other entity; however, several alternatives may be included in one response. For purposes of this requirement, “partnership” shall mean, and is limited to, a legal partnership formed under one or more of the provisions of the California or other state’s Corporations Code or an equivalent statute.

All other information regarding the bid responses will be held as confidential until such time as the County Selection Committee has completed its evaluation, a recommended award has been made by the County Selection Committee, and the contract has been fully negotiated with the intended awardee named in the recommendation to award/non-award notification(s).  The submitted proposals shall be made available upon request no later than five calendar days before the recommendation to award and enter into a contract is scheduled to be heard by the Board of Supervisors.  All parties submitting proposals, either qualified or unqualified, will be sent recommend to award/non-award notification(s), which will include the name of the Bidder to be recommended for award of this project.  In addition, award information will be posted on the County’s “Contracting Opportunities” website, mentioned above.

Each bid received, with the name of the Bidder, shall be entered on a record, and each record with the successful bid indicated thereon shall, after the award of the order or contract, be open to public inspection.

California Government Code Section 4552:  In submitting a bid to a public purchasing body, the Bidder offers and agrees that if the bid is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2, commencing with Section 16700, of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the Bidder for sale to the purchasing body pursuant to the bid.  Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the Bidder.

Bidder expressly acknowledges that it is aware that if a false claim is knowingly submitted (as the terms “claim” and “knowingly” are defined in the California False Claims Act, Cal. Gov. Code, §12650 et seq.), County will be entitled to civil remedies set forth in the California False Claim Act.  It may also be considered fraud and the Contractor may be subject to criminal prosecution.

The undersigned Bidder certifies that it is, at the time of bidding, and shall be throughout the period of the contract, licensed by the State of California to do the type of work required under the terms of the Contract Documents.  Bidder further certifies that it is regularly engaged in the general class and type of work called for in the Bid Documents.

The undersigned Bidder certifies that it is not, at the time of bidding, on the California Department of General Services (DGS) list of persons determined to be engaged in investment activities in Iran or otherwise in violation of the Iran Contracting Act of 2010 (Public Contract Code Section 2200-2208).

It is understood that County reserves the right to reject this bid and that the bid shall remain open to acceptance and is irrevocable for a period of 180 days, unless otherwise specified in the Bid Documents.

## RESPONSE FORMAT

Bid responses are to be straightforward, clear, concise and specific to the information requested.

In order for bids to be considered complete, Bidder must provide responses to all information requested.  See Exhibit A – Bid Response Packet.

Bid responses, in whole or in part, are NOT to be marked confidential or proprietary.  County may refuse to consider any bid response or part thereof so marked.  Bid responses submitted in response to this RFP may be subject to public disclosure.  County shall not be liable in any way for disclosure of any such records.  Please refer to the County’s website at: http://www.acgov.org/gsa/departments/purchasing/policy/proprietary.htm for more information regarding Proprietary and Confidential Information policies.

### EXHIBIT A

BID RESPONSE PACKET

INSTRUCTIONS

- As described in the submittal of bids section of this RFP, Bidders must submit an electronic copy of the bid in PDF (with OCR preferred).  The electronic copy must have all appropriate pages signed (().

- Each page of the Bid Response Packet must be submitted as PDF attachment(s) with all required information included and documents attached;  any pages of the Bid Response Packet not applicable to the Bidder must be submitted with such pages or items clearly marked “N/A” or the bid may be disqualified as incomplete.

- Bidders shall not modify the Bid Response Packet or any other County-provided document unless instructed to do so.  Modifications Bidders are instructed to make include:

  - On the cover page of the Bid Response Packet, Bidders must replace the information in BLUE font (name of Bidder organization, primary contact name, etc.).

- Bidder must quote price(s) as specified in the RFP, including any addendums.

- Bidders that do not comply with the requirements, and/or submit incomplete bid packages, are subject to disqualification and their bids being rejected.

- If a Bidder is making any clarifications, or taking exception to policies or specifications of this RFP, these must be submitted in the Exceptions and Clarifications form of the Bid Response Packet in order for the bid response to be considered complete.

Date of Submission

Name of Bidding Organization

Primary Contact Name

Primary Contact Title

Address 1

Address 2

City, State Zip Code

Phone Number

Email Address

### BID RESPONSE PACKET

Housing Element RFP

#### BIDDER INFORMATION

Official Name of Bidder:

Street Address Line 1:

Street Address Line 2:

City:      		State:      		Zip Code:

Webpage:

Type of Entity / Organizational Structure (check one):

Corporation		 Joint Venture

Limited Liability Partnership		 Partnership

Limited Liability Corporation		 Non-Profit / Church

Other:

Jurisdiction of Organizational Structure:

Date of Organizational Structure:

Federal Tax Identification Number:

DIR Contractor Registration Number:

Primary Contact Information:

Name / Title:

Telephone Number:      		Alternate Number:

E-mail Address:

#### BIDDER ACCEPTANCE

- The undersigned declares and agrees that the Bid Documents, including, without limitation, the RFP, Q&A, Addenda, and Exhibits have been read and accepted.

- The undersigned is authorized, offers, and agrees to furnish the articles and/or services specified in accordance with the Specifications, Terms & Conditions of the Bid Documents of the Housing Element RFP.

- The undersigned has reviewed the Bid Documents and fully understands the requirements in this Bid including, but not limited to, general County requirements, and that each Bidder who is awarded a contract shall be, in fact, a prime Contractor, not a subcontractor, to County, and agrees that its Bid, if accepted by County, will be the basis for the Bidder to enter into a contract with County in accordance with the intent of the Bid Documents.

- The undersigned agrees to the following terms, conditions, certifications, and requirements found on the County’s website:

- Debarment / Suspension Policy

[http://www.acgov.org/gsa/departments/purchasing/policy/debar.htm]

- Iran Contracting Act (ICA) of 2010

[http://www.acgov.org/gsa/departments/purchasing/policy/ica.htm]

- General Environmental Requirements

http://www.acgov.org/gsa/departments/purchasing/policy/environ.htm

- Small Local Emerging Business Program

[http://acgov.org/auditor/sleb/overview.htm]

- First Source

[http://acgov.org/auditor/sleb/sourceprogram.htm]

- Online Contract Compliance System [http://acgov.org/auditor/sleb/elation.htm]

- General Requirements

[http://www.acgov.org/gsa/departments/purchasing/policy/genreqs.htm]

- The undersigned acknowledges that Bidder is and will remain in good standing in the State of California, with all the necessary licenses, permits, certifications, approvals, and authorizations necessary to perform all obligations in connection with this RFP.

- It is the responsibility of each Bidder to be familiar with all of the specifications, terms and conditions and, if applicable, the site condition.  By the submission of a Bid, the Bidder certifies that if awarded a contract they will make no claim against the County based upon ignorance of conditions or misunderstanding of the specifications.

- Patent indemnity:  Vendors who do business with the County shall hold the County of Alameda, its officers, agents and employees, harmless from liability of an nature or kind, including cost and expenses, for infringement or use of any patent, copyright or other proprietary right, secret process, patented or unpatented invention, article or appliance furnished or used in connection with the contract or purchase order.

- The undersigned acknowledges ONE of the following (please check only one box):

Bidder is not local to Alameda County and is ineligible for any bid preference; or

Bidder is a certified SLEB at the time of bid submittal and is requesting 10% bid preference; (Bidder must check the first box and provide its SLEB Certification Number in the SLEB INFORMATION SHEET); or

Bidder is LOCAL to Alameda County and is requesting 5% bid preference, and has attached the following documentation to this Exhibit:

- Copy of a verifiable business license, issued by the County of Alameda or a City within the County; and

- Proof of six months business residency, identifying the name of the vendor and the local address.  Utility bills, deed of trusts or lease agreements, etc., are acceptable verification documents to prove residency.

SIGNATURE: (

Name/Title of Authorized Signer:

Dated this      		day of      		20

#### TABLE OF CONTENTS

Instructions:  Bidder shall remove this page and replace it with a Table of Contents listing the individual sections of the proposal and their corresponding page numbers.  The page(s) inserted shall be clearly marked Table of Contents.

#### LETTER OF TRANSMITTAL

Instructions:  Bidder shall remove this page and replace it with a Letter of Transmittal.  The letter shall include a description of Bidder’s capabilities and approach in providing its services to the County, and provide a brief synopsis of the highlights of its proposal and overall benefits to the County.  The page(s) inserted shall be clearly marked Letter of Transmittal.

Maximum Length:  2 pages

#### BUDGET DETAIL AND/OR COST NARRATIVE

Instructions:  This page must be included as part of the Bid Response Packet.  Following this page, Bidder shall provide a Budget Detail.

The Budget Detail shall provide a breakdown of project cost(s).  Bidders may use a budget template of their own choice; however, all cost attributed to the project that will paid for under the awarded contract MUST be listed and described in the Budget Detail.

At minimum, the Bidder must detail:

- The work to be performed and all associated costs.

- If coordination with County personnel is needed, it should also be delineated in the Budget Detail.

- The work to be performed should clearly match up with work performed in the Description of Proposed Services.

- The positions of all individuals that will perform the services;

- Names of Key Personnel may be listed whenever appropriate

- The estimated number of hours for each individual, corresponding hourly rates per individual and extended costs.

- Community engagement outreach efforts may involve amenities for participants (e.g., food, childcare, and other participation-related costs) and services (e.g., translation, interpretation, and transcription). A complete bid response will include line items that account for such expenditures.

Maximum Length:  none

#### DESCRIPTION OF PROPOSED SERVICES

Instructions:  This page must be included as part of the Bid Response Packet.  Following this page, Bidder shall provide a Description of Proposed Services.

The Description of Proposed Service shall describe the overall services.  The Bidder must address how they will meet or exceed each requirement listed in Section E (Specific Requirements) and Section F (Deliverables/Reports).

At minimum, the Bidder must include the following details:

- Describe the program’s desired overall goals, anticipated outcomes, measurable objectives, and key tasks including the key personnel responsible for achieving them.

- Detail existing data collection infrastructure and demonstrate ability to interface with County’s database(s) and/or provide reporting data to the County for maximum efficiency.

- Explain any special resources, procedures, or approaches that make the services of Bidder particularly advantageous to the County.

- Identify any limitations or restrictions of Bidder in providing the services that the County should be aware of in evaluating its Response to this RFP. (Please note any requests for exceptions or clarifications MUST be identified on Exceptions and Clarification form below and the County is under no obligation to accept any exceptions or clarifications and any such exceptions and clarifications may be a basis for bid disqualification.)

Maximum Length:  none

TABLE OF KEY PERSONNEL

Instructions:  This page must be included as part of the Bid Response Packet.  Following this page, Bidder shall provide a Table of Key Personnel.  The table shall include all key personnel associated with the RFP.

This table must include all key personnel who will provide services to the County, including collaborating partners.  The table must include the following information for each key person:

- The person’s relationship with Bidder, including job title and years of employment with Bidder;

- Work contact information including, but not limited to, the following:  work address, office telephone number, mobile work number, and e-mail address;

- The role that the person will play in connection with the RFP;

- Educational background; and

- Related experience on similar projects, certifications, and merits.

If a Bidder collaborates with any other partners or subcontractors, Bidder shall identify subcontractors, subcontractor qualifications, and how they plan to work together. Bidder(s) shall identify any existing agreements or MOUs between the Bidder(s) and proposed collaborator(s).

Maximum Length:  There is no limit to the table.  There is, however, a 2-page limit per résumé or curriculum vitae.

#### IMPLEMENTATION PLAN AND SCHEDULE

Instructions:  This page must be included as part of the Bid Response Packet.  Following this page, Bidder shall provide an Implementation Plan and Schedule.

In conjunction with the Description of Proposed Services and the Budget Detail, Bidder must include an Implementation Plan and Schedule that specifically addresses the following:

- A timeline of project goals, measurable outcomes, and benchmark activities related to the provision of required services—as well as the key personnel assigned to each.

The Implementation Plan and Schedule should provide a clear picture of what the County can expect, and when to expect it, upon starting the contract.  Bidders should also take into consideration the information and questions contained in the Evaluation Criteria in preparing the Implementation Plan and Schedule.

Maximum Length:  None

#### REFERENCES

Instructions:  On the following pages are the templates that Bidders must use to provide references.  Bidders are to provide a list of five references.  References must be satisfactory as deemed solely by County.  Services or goods provided by Bidder to the references should have similar scope, volume and requirements to those outlined in these specifications, terms and conditions.

Bidders must verify that the contact information for all references provided is current and valid.  If a reference cannot be contacted it may affect the qualification and scoring of Bidders submission.

Bidders are strongly encouraged to notify all references that the County may be contacting them to obtain a reference.

The County may contact some or all of the references provided in order to determine Bidder’s performance record on work similar to that described in this request.  The County reserves the right to contact references other than those provided in the Response and to use the information gained from them in the evaluation process.

REFERENCES

Housing Element RFP

Bidder Name:

| Company Name: | Contact Person: |
| --- | --- |
| Address: | Telephone Number: |
| City, State, Zip: | E-mail Address: |
| Services Provided / Date(s) of Service: |

| Company Name: | Contact Person: |
| --- | --- |
| Address: | Telephone Number: |
| City, State, Zip: | E-mail Address: |
| Services Provided / Date(s) of Service: |

| Company Name: | Contact Person: |
| --- | --- |
| Address: | Telephone Number: |
| City, State, Zip: | E-mail Address: |
| Services Provided / Date(s) of Service: |

| Company Name: | Contact Person: |
| --- | --- |
| Address: | Telephone Number: |
| City, State, Zip: | E-mail Address: |
| Services Provided / Date(s) of Service: |

| Company Name: | Contact Person: |
| --- | --- |
| Address: | Telephone Number: |
| City, State, Zip: | E-mail Address: |
| Services Provided / Date(s) of Service: |

#### EXCEPTIONS AND CLARIFICATIONS

Instructions:  On the following page is the Exceptions and Clarifications form.  Bidders must use this form to identify any and all exceptions and/or clarifications to the RFP and associated Bid Documents.

THE COUNTY IS UNDER NO OBLIGATION TO ACCEPT ANY EXCEPTIONS AND CLARIFICATIONS ANY SUCH EXCEPTIONS AND CLARIFICATIONS MAY BE A BASIS FOR BID DISQUALIFICATION.

EXCEPTIONS AND CLARIFICATIONS

Housing Element RFP

Bidder Name:

List below requests for exceptions and clarification, if any, to the RFP and associated Bid Documents, and submit with your bid response.

The County is under no obligation to accept any exceptions and clarifications and such exceptions and clarifications may be a basis for bid disqualification.

| Reference to: | Description |
| --- | --- |
| Page No. | Section | Item No. |  |
| p. 23 | D | 1.c. | Vendor takes exception to… |

*Use additional pages as necessary

#### SLEB INFORMATION SHEET

Instructions:  On the following page is the SLEB Information Sheet.  Every Bidder must fill out and submit a signed SLEB Information Sheet, indicating their SLEB certification status.  If Bidder is not certified, the information sheet must be completed with the name, identification information, and goods/services to be provided by the CERTIFIED SLEB partner(s) with whom the Bidder will subcontract to meet the County SLEB participation requirement.  The Exhibit must be signed by EACH of the named CERTIFIED SLEB(s) that will be subcontractors.

SLEB certification must be complete at the time of bid submittal for SLEB primes and SLEB subcontractor(s).

- For SLEB Subcontracting Questions: Please contact the General Services Agency-Office of Acquisition Policy - Ratha Chuon, ratha.chuon@acgov.org, (510) 208-9617.

- For questions/information regarding SLEB certification including requirements, please contact the Auditor-Controller Agency, Office of Contract Compliance & Reporting – SLEB Certification Unit at (510) 891-5500.

SMALL LOCAL EMERGING BUSINESS (SLEB)

INFORMATION SHEET

Housing Element RFP

In order to meet the Small Local Emerging Business (SLEB) requirements of this RFP, all Bidders must complete this form.

Bidders that are not certified SLEBS (for definition of a SLEB see http://acgov.org/auditor/sleb/overview.htm) are required to subcontract with a SLEB for at least 20% of the total estimated bid amount in order to be eligible for contract award.  SLEB subcontractors must be independently owned and operated from the prime Contractor with no employees of either entity working for the other.  A copy of this form must be submitted for each SLEB that the Bidder will subcontract with, as evidence of a firm contractual commitment to meeting the SLEB participation requirement.

Bidders are encouraged to form a partnership with a SLEB that can participate directly with this contract.  One of the benefits of the partnership will be economic, but this partnership will also assist the SLEB to grow and build capacity to eventually bid as a prime on their own.

Once a contract has been awarded, substitutions of the named subcontractor(s) are not allowed without prior written approval from the Auditor-Controller, Office of Contract Compliance & Reporting (OCCR).

County departments, prime and subcontractors are required to use the web-based Elation Systems to monitor SLEB subcontractor compliance with Elation Systems: http://www.elationsys.com/elationsys/.

BIDDER IS A CERTIFIED SLEB (sign at bottom of page) SLEB BIDDER Business Name: SLEB Certification #: SLEB Certification Expiration Date: NAICS Codes Included in Certification:

OR

BIDDER IS NOT A CERTIFIED SLEB and will subcontract % with the SLEB named below for the following goods/services: SLEB Subcontractor Business Name: SLEB Certification #: SLEB Certification Expiration Date: SLEB Certification Status: Small / Emerging NAICS Codes Included in Certification: SLEB Subcontractor Principal Name: SLEB Subcontractor Principal Signature: ( Date:

Upon award, Bidder (the prime Contractor) and all SLEB subcontractors agree to register and use the secure web-based ELATION SYSTEMS. ELATION SYSTEMS will be used to submit SLEB subcontractor participation including, but not limited to, subcontractor contract amounts, payments made, and confirmation of payments received.

Bidder Printed Name/Title: ____________________________________________________________________________

Street Address: ________________________________________City_____________State______ Zip Code______

##### Bidder Signature: (								Date:

#### CREDENTIALS

Instructions:  This page must be included as part of the Bid Response Packet.  Following this page, Bidders are to provide proof of any permits, licenses, and/or professional credentials necessary to supply product and perform services as specified in this RFP.

### EXHIBIT B

### EXHIBIT C

COUNTY OF ALAMEDA MINIMUM INSURANCE REQUIREMENTS